## UAP
COUNT | PROVIDER NAME | LOCATION | STATUS | FINAL COMMANT | LOCATION | PERSON | CONTACT | REQUEST MONTH | SO
1 | Pope John’s Hospital | OYAM | Pending | There is a computer available. Equipment will be sent for remote installation | Northern | Walter Anguzu & Sr. Saraphine/Bobby | 0781-448-112/0782505454 /0777808874 | 2019-05-01 | Kevin
2 | ECOPHRARM PHARMACY KIRUDU | KAMPALA | Pending | Advised by Peter to halt the installation | CENTRAL | Peter | 782618655 | 2019-07-01 | Sseninde
3 | City Ambulance | KAMPALA | Pending | Not installable. Provider does not have computers | CENTRAL |  |  |  | Francis

## AAR
COUNT | TOWN | PROVIDERS NAME | STATUS AS AT 1/1/2020 | FINAL COMMENT | LOCATION | CONTACT PERSON | TEL. CONTACTS | SO
1 | OYAM | Pope John’s Hospital | There is a computer available. Equipment will be sent for remote installation | Installable | NORTHERN | Walter Anguzu & Sr. Saraphine/Bobby | 0781-448-112/0782505454 /0777808874 | Kevin
2 | Zombo | Nyapia misssion hospital zombo | Equipment to be sent in the third week of July 2020 | Installable | NORTHERN | Dr Omara and Dr Okello | (0783-725018) and (0780-640685) | Bashir
3 | MPIGI | ST MONICA HCIII KATENDE MPIGI | To be installed in the third week of July 2020 | Installable | CENTRAL | Milverd | 0700-569822 | Bosco
4 | KOBOKO | Carlos Medical Centre Koboko | Equipment to be sent in the second week of August 2020 | Installable | NORTHERN | Dr. Charles | 788101826 | Kevin
5 | Kabongo | Trinity Medical Centre Karenga | Provider will be in Kampala on Wed-5/8/2020 for installation | Installable | KARAMOJA | Dr. Okite | 0782-482300
6 | KALANGALA | Eunice Memorial Medical Centre | Installation to be planned after getting the most viable travel option to Kalangala | Installable | CENTRAL | Dr. Suubi | 0776-945534
7 | Wakiso | St. Catherines Medicare Najjera | o be installed on 4/8/20 | Installable | CENTRAL
8 | Wakiso | Family Medical Centre Kasangati | To be installed week starting 10/8/2020 | Installable | CENTRAL | Dr. Abel Semakula | 0772-638635

## SANCARE
COUNT | SERVICE PROVIDER | STATUS | LOCATION | DISTRICT | STATUS | REQUEST MONTH | SO | CONTACT PERSON | CONTACT
1 | NILE MEDICAL CENTER | NOT INSTALLABLE | NORTHERN |  | Available computer does not meet requirements for installation | 2019-04-01 | Kevin
2 | VIRA MARIA HOSPITAL | NOT INSTALLABLE | Central |  | No computer yet | 2019-08-01 | Rachal |  | 776179288
3 | Kawolo Hospital Private wing | Not installable | Central |  | No MTN network in the area | 2020-01-01 | Beatrrice | Dr Kiberu Joshua | 773 441 481
4 | SPECTRUM MEDICAL SERVICES | INSTALLABLE | NORTHERN |  | Remote installation will be done, equipment will be sent via bus | 2020-01-01 | Kevin | DR GEORGE BOKHA | 772869894
5 | GREAT MISSION MEDICAL CENTER | INSTALLABLE | Central | SSEMBABULE | To be installed on 4/8/2020 | 2020-08-03 | Rachal | Dr. Gumisiriza John | 752690042
6 | HOUSE OF HOLLY FAMILY NURSING HOME | INSTALLABLE | Central |  | To be installed on 4/8/2020 | 2020-08-03 | Rachal | Dr. Mwebe Masembe | 755243681
7 | PAG HOSPITAL LIRA | INSTALLABLE | Eastern | LIRA | Remote installation will be done, equipment will be sent via bus | 2020-08-01 | Bosco | Director | 0773535689/0779512318
8 | MIDAS TOUCH KUMI | INSTALLABLE | Eastern | KUMI | Remote installation will be done, equipment will be sent via bus | 2020-08-01 |  | Dr. Titus Opegu | 0702513427, 0780530090

## IML
COUNT | NAME OF FACILITY | SO | STATUS | FINAL COMMENT | COMMENT | LOCATION | SERVICE RENDERED | PHYSICAL ADDRESS | CONTACT PERSON / PEOPLE | CONTACT NUMBERS

## FAWE
Count | Provider | Location | Status

## IAA
COUNT | PROVIDER NAME | LOCATION |  | Stautus | Comment
1 | Afya Clinic Kihihi | Western Lower | Kanungu | Equipment will be sent to the provider and installation will be done remotely

## MINET
Count | PROVIDER | COMMENT | CONTACT | PERSON | LOCATION | STATUS | SO
1 | ST COSMAS ET DOMIANUS CLINIC | No computer | 77606497 | Dr. Domianus | Kisoro | Not installable | Sseninde
2 | Oakspring specialist clinic | Provider has not provided any update about windows upgrade |  |  | Kampala | Not installable | Francis
3 | Olive Pharmacy Kampala | Not ready | 0774 425 004 |  | Kampala | Not installable | Francis
4 | Olive Pharmacy Mbarara | Not ready | 0774 425 004 |  | Mbarara | Not installable | Emma S
5 | ASG Eye hospital | To be insalled week starting 10/8/2020 | 0705422852- | Osler Kasule | Kampala | Installable | Betrice
6 | Community Eye Clinic Mbarara | No contact

## PRUD
Count | Provider | Customer | Contact | Number | Location | Status |  | Request month
1 | Shifa clinic in Kapchorwa | PRU | Dr Siraji Masai | 0772-618531 | KAPCHORWA | To be engaged in the second week of July to find out if the computer is now available | Pending
2 | Malcom Heaalth Naalya | PRU | Bruhan | 700795972 | KAMPALA | Computers not ready for installation | Pending
3 | Malcom Medical Center Kibuye | PRU | Bruhan | 700795972 | KAMPALA | Computers not ready for installation | Pending
4 | Malcom Medical Center Kisasi | PRU | Bruhan | 700795972 | KAMPALA | Computers not ready for installation | Pending

## ICEA
Count | Provider | Location | District | STATUS | SO | REQUEST MONTH | CONTACT PERSON | PHONE NUMBER
1 | GUARDIAN PHARMACY JINJA | Eastern | Jinja | Installable | Beatrice | July |  | 0778139879
2 | GUARDIAN PHARMACY MUNYONYO | Central | Kampala | Installable | Ssenninde | July |  | 0778140235
3 | GUARDIAN PHARMACY MBARARA | Werstern Lower | Mbarara | Installable | Ssenninde | July |  | 0771422552
4 | GUARDIAN PHARMACY NTINDA | Central | Kampala | Installable | Francis | July |  | 0778139871
5 | GUARDIAN PHARMACY WANDEGEYA | Central | Kampala | Installable | Beatrice | July |  | 0778138629
6 | GUARDIAN PHARMACY KANSANGA | Central | Kampala | Installable | Rachal | July |  | 0778139724
7 | GUARDIAN PHARMACY KISEMENTI | Central | Kampala | Installable | Francis | July |  | 0778134960
8 | GUARDIAN PHARMACY BUNGA | Central | Kampala | Installable | Rachal | July |  | 0778139680
9 | GUARDIAN PHARMACY KABALAGALA | Central | Kampala | Installable | Rachal | July |  | 0778132796
10 | GUARDIAN PHARMACY KITINTALE | Central | Kampala | Installable | Kevin | July |  | 0778139589
11 | FRIECCA PHARMACY NTINDA | Central | Kampala | Installed | Francis | July |  | 774881990

## SHU
COUNT | PROVIDER NAME | LOCATION | STATUS | CSE | LOCATION

## PWC
COUNT | PROVIDER NAME | LOCATION | STATUS | FINAL COMMANT | PERSON | CONTACT | REQUEST MONTH | SO

## BAMBI
COUNT | PROVIDER NAME | LOCATION | STATUS | FINAL COMMANT | PERSON | CONTACT | REQUEST MONTH | SO

## SUMMARY
SUMMARY
LOCATION | UAP | AAR | ICEA | SHU | IAA | IML | SANCARE | MINET | BAMBI | PWC | NM | PRU | TOTAL
CENTRAL | 2 | 4 | 9 | 0 | 0 | 0 | 4 | 2 | 0 |  | 0 | 2 | 23
LOWER WESTERN | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 3 |  |  | 0 | 0 | 5
UPPER WESTERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
NORTHERN | 1 | 3 | 0 | 0 | 0 | 0 | 2 |  |  |  | 0 | 0 | 6
EASTERN | 0 | 0 | 1 | 0 | 0 | 0 | 2 |  |  |  | 0 | 1 | 4
KARAMOJA | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1
TOTAL | 3 | 8 | 11 | 0 | 1 | 0 | 8 | 5 | 0 | 0 | 0 | 3 | 39
INSTALLABLE PROVIDERS
| UAP | AAR | ICEA | SHU | IAA | IML | SANCARE | MINET | BAMBI | PWC | NM | PRU | Total
| 1 | 8 | 10 | 0 | 1 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 26